## Sheet1
Dimension Name | Level | Unique ID | Capability | Acceptance Criteria | Predecessor
Strategy Alignment | Traveller | 1 | Any alignment to Strategy is coincidental or opportunistic | There is no explicit definition of the strategy in the teams. The team do not have a shared accessible document where they can see the strategy. Alignement is purely coincidental and not deliberate | 0
Strategy Alignment | Artisan | 2 | Upfront engagement with stakeholders to ensure Business and Technical Alignment | Business and Technology stakeholders are both present in the PI Planning sessions. The team engages with both the business and technical stakeholders for the strategy and goal setting. | 1
Strategy Alignment | Artisan | 3 | The product/project vision is explicitly aligned to strategy | The team has access to the product/project vision as well as the strategy. There is clear visualisation of how the vision aligns to the strategy and all the team members can access the document that links the two. | 1
Strategy Alignment | Artisan | 4 | Post implementation review to confirm strategy alignment | There is a review of alignement to strategy in the Post implementation PI sessions but no review during the implementation stage. | 1
Strategy Alignment | Expert | 5 | Occasional engagement with stakeholders throughout delivery cycle to review business and technical alignment | The team engages with the stake holders during implementation to ensure business and technical alignment. This engagement is however occasional for example once every 2 months or so. | 2,3,4
Strategy Alignment | Expert | 6 | Backlog items are created to deal with strategy alignment issues | There are stories in the backlog to ensure strategy alignment. Also a RAID card to ensure the team is always re-aligning in case of deviation. Strategy alignment issues can be tracked and managed. | 0
Strategy Alignment | Professional | 7 | Frequent engagement with Stakeholders to review Business and technical alignment | The team is in frequent communication with the stakeholders to ensure alignment to the strategy. This has become part of the sprint planning/retrospective sessions and happens every sprint. | 5
Strategy Alignment | Professional | 8 | Team presents product to Architecture and Design teams with the intent of picking up alignment issues | Meetings happen between team, architecture and design where necessary to ensure alignment every sprint. | 5
Strategy Alignment | Professional | 9 | Metrics to measure strategy elements defined and tracked | Team has metrics visible on their wall defined for strategy alignment and these are tracked and measured. There is prioritisation of the tasks with the team deliverables. | 0
Strategy Alignment | Master | 10 | All major strategy alignment backlog items have been resolved | The team has resolved all the strategy alignment items that were defined in their backlog. | 6
Strategy Alignment | Master | 11 | All requirements are attached to business metric | The user stories on the team walls can be tracked and traced to a business metric, which the team members are aware of. | 9
Strategy Alignment | Master | 12 | Metrics are tracked over time and improvements targets are set and achieved | Strategy metrics are constantly tracked, monitored and updated where required. Separate user stories are written for improvements and are prioritized in the backlog items. | 9
Strategy Alignment | Master | 13 | Team independently innovates by creating new features or optimisations in support of or extending the strategy. | There is visible innovation/optimisation in the team in line with the strategy. These are captured as cards on the teams story wall and extra achievements in the scope management tool. | 9
Planning and Requirements | Traveller | 14 | Team is not involved in estimates | The estimation of the work is done without the team's involvement and passed down to the team. The team works on tasks without changing the estimated time/effort required to complete the tasks. The team has no control over the estimates. | 0
Planning and Requirements | Traveller | 15 | No Specific prioritization of requirements | The tasks in the backlog are not prioritized. Business owners add stories to the backlog without prioritizing the work. Team delivers the tasks eventhough they are not prioritized. | 0
Planning and Requirements | Traveller | 16 | Iteration lengths are erratic and based on the amount of functionality | The iterations exists in the team but there are no fixed iteration lengths. The iteration time frames get modified based on the functionality the team wants to deliver. The team has the concept of iterations though. | 0
Planning and Requirements | Traveller | 17 | The team does not know their velocity | The team delivers functionality every iteration but is unable to estimate before the iteration kicks-off how much work the team can do. The team has not been tracking the velocity. | 0
Planning and Requirements | Traveller | 18 | No Stakeholder management in place | The team knows the stakeholders, however every steakholder can modify the tasks the team is working on without it being coordinated. | 0
Planning and Requirements | Artisan | 19 | Team performs estimates up-front | Team estimates all of the tasks for the whole project up-front post the PI planning session rather than iteratively. If the team estimates all the stories upfront then this tasks can be marked as completed. | 14
Planning and Requirements | Artisan | 20 | Requirements are prioritized based on business value | The requirement items in the backlog are prioritized by the business stakeholder. It should be noted that the prioritization is not based on the technical team's decision but based on the business stakeholder to ensure alignment with strategy. | 15
Planning and Requirements | Artisan | 21 | Iteration lengths are fixed | This tasks superceeds item 16. This tasks is marked as complete when the team has fixed iteration lengths rather than iteration lengths that change based on functionality. On completing this task, item 16 can also be marked as completed if it is not yet marked as such. | 16
Planning and Requirements | Artisan | 22 | The team knows their velocity | Team has measured their velocity and this is visual on their wall. This superceeds item 17. If the team measures and monitors their velocity item 17 can also be marked as completed if it wasn't yet marked as such. | 17
Planning and Requirements | Artisan | 23 | Stakeholders have been identified and a communication plan is in place | When team starts having a coordinated stakeholder management plan, item 18 can be marked as completed if it has not been marked as such. Team has a well defined plan which everyone is aware of on stakeholder communication/interaction. | 18
Planning and Requirements | Expert | 24 | Team performs estimation iteratively | This task is complete when the team stops estimating all of the work up-front but rather estimates the work iteratively. This superceeds item 19. Team estimates work in small batches as opposed to a big bang estimation approach. | 19
Planning and Requirements | Expert | 25 | When the team estimates the estimates include all activities to reach 'Done'. | Team has a definition of what 'Done' is, which is understood by everyone in the team. All the estimates take into account activities required to get to Done, which may include amongst others testing, deployment etc. | 19
Planning and Requirements | Expert | 26 | The MVP and MVPS have been identified | There is a clearly defined MVP, which is communicated and radiated to all the team members and the stakeholders. | 20
Planning and Requirements | Expert | 27 | The teams velocity is predictable | The team velocity over a few iterations is consistent within a tolerance of 1-2 velocity points. Team confidently delivers the velocity committed to. | 22
Planning and Requirements | Expert | 28 | All backlog items are sized by the teams | Backlog items planned for each iteration has been estimated by the team working on the functionality. | 0
Planning and Requirements | Expert | 29 | Stakeholders attend showcase | The stakeholders are always present for the showcases. | 23
Planning and Requirements | Professional | 30 | Team tracks performance against estimates | The team reviews the estimates every end of the iteration to improve on their estimation accuracies for future iterations. There is a document available for any estimated discrepancies | 24,25
Planning and Requirements | Professional | 31 | Requirements are developed on a just –in –time basis | Acceptance criteria are used for the stories to be worked on. The requirements are not done many months before the work is performed but rather one or two iterations in advance. | 26
Planning and Requirements | Professional | 32 | Analytics are implemented to determine the effectiveness of requirements | A lists is maintained of stories that have been completed as well as stories that have gone through the flow and had to be sent back to analysis after showcase. | 26
Planning and Requirements | Professional | 33 | The amount of functionality for each iteration is determined by the teams velocity | The team's velocity drives the amount of work the team commits to and this is not influenced by the amount of functionality the stakeholders want to push on the team. | 27
Planning and Requirements | Professional | 34 | Technical debt and defects are tracked on the backlog and form part of the estimated team velocity | Team caters for technical debt as part of the normal workflow lifecycle. Stories are created for such technical debt in the backlog and these are prioritised, planned and executed in the same flow as other business relevant stories. Stakeholders are informed of the significance and impact of the technical debt. | 28
Planning and Requirements | Professional | 35 | Stakeholders actively participate in retrospective | The retrospectives are run every iteration and the stakeholders are present in the retrospective. Stakeholders contribute to retrospectives and action items which are allocated to them are tracked by the team on the team wall. | 29
Planning and Requirements | Master | 36 | Requirements are defined with an expected outcome with an objective measure | The requirements on the backlog have acceptance criteria with clear outcomes and objective measures of what success is. | 31,32
Planning and Requirements | Master | 37 | Release planning is performed based on the teams current velocity | The release planning for future releases takes into account the team's per iteration velocity to scope the amount of work possible for the release. | 33,34
Planning and Requirements | Master | 38 | A process is in place (e.g. a formal beta program) to allow extended stakeholders and customers to evaluate the software and provide feedback. | Process exists and is understood by all the stakeholders on how to give feedback about the software and how to raise enhancements required. These are tracked in the story management tool and used in the PI pre-planning sessions. | 35
Coding Practices | Traveller | 39 | No standards or mechanism's for ensuring code quality | The team writes code without any agreed standards for quality. | 0
Coding Practices | Artisan | 40 | Guidelines and/or standards are defined. | There are coding guidelines and standards defined. These are documented and easily accessible by any team member or newly joined team member. | 39
Coding Practices | Artisan | 41 | Consistent training process for new team members is in place | There is an onboarding plan and document for new members who join the team. The document is easily accessible by all and can be used as further reference material. | 0
Coding Practices | Expert | 42 | There are mechanism’s in place to ensure that standards are followed | Code review is used to enforce the standards. Automated tools like JSLint or JSHint for Javascript, Checkstyle for Java, and lint are used to ensure the standards are followed. Static analysis dashboards exists for the code through applications like SonarQube | 40
Coding Practices | Expert | 43 | Process's and practices are understood and followed by all | The coding practices and processes are documented and the team is aware of where to access them. | 41
Coding Practices | Expert | 44 | Metrics are defined but not necessarily reviewed and acted on | The code metrics such as test coverage and cyclomatic complexity are defined and readily available to the team. These metrics are however not reviewed to improve the coding practices. | 0
Coding Practices | Expert | 45 | The team proactively improves the code | The team plans for refactoring slack for each iteration. The team maintains a graph of historic code metrics. | 0
Coding Practices | Professional | 46 | Code metrics are part of build automation and continuous integration | The build automation tool generates the code quality metrics which can be automatically fed to SonarQube or used for representative dashboards. | 44
Coding Practices | Professional | 47 | Code metrics are tracked for trends and adjustments made on a continuous basis | The team maintains a graph of historic code metrics. The code quality metrics are addressed by the team every iteration. | 44
Coding Practices | Professional | 48 | The team regularly performs katas with the objective of improving their skills | There is time set aside every month for some code katas to help improve the team coding practices skills. Katas are planned in the release plans and delivery plans. | 45
Coding Practices | Professional | 49 | Code is regularly refactored as part of the iteration | Refactoring is a regular discipline of the team. The team follows a "Leave The Code Better Than You Found It" principle. | 45
Coding Practices | Master | 50 | Standards and Practices are regularly reviewed and updated | The team reviews the standards and practices every iteration. Quality threshold metrics are increased and the standards are optimized. | 42
Coding Practices | Master | 51 | Processes and Practices are regularly reviewed and updated | The team reviews the processes and practices every iteration. Quality threshold metrics are increased and the processes are optimized. | 43
Coding Practices | Master | 52 | The code metrics are assessed and backlog items created to drive improvement | There are continuous assessments of the code metrics to ensure the team is aligned to the quality standards. Backlog items are created to address gaps identified from the code metrics perspective and these are tracked and prioritized. | 46,47
Coding Practices | Master | 53 | Technical debt is minimized | Technical debt items are tracked and the code static analysis metrics are tracked to show progress with technical debt reduction. | 0
Continuous Integration | Traveller | 54 | No version management of artefacts and reports | Artefacts, code and report are kept in developer machines. There is no use of a version management technology. | 0
Continuous Integration | Traveller | 55 | Deployments & Rollbacks are manual | All deployments and application rollbacks are done manually by experienced developers or operations. | 0
Continuous Integration | Traveller | 56 | Build is performed manually and infrequently. | There is a build but this is done through manual steps. Builds happen infrequently in big batches as opposed to incrementally in very small batches. The team needs to make sure the builds are done more frequently and automated. | 0
Continuous Integration | Traveller | 57 | Build is owned by a specific person | The process of creating a build artefact is known by a specific person in the team. Absence of this person in the team leads to the application not being able to be deployed. Collective ownership of the process needs to be promoted with more team members knowing how to build the application. | 0
Continuous Integration | Traveller | 58 | Testing is manual | All the testing performed are manual, predominantly exploratory type tests. Team needs to start implementing automated tests. | 0
Continuous Integration | Traveller | 59 | Development environments manually provisioned and shared between teams | The environments required by the development teams (developers, QAs, UAT etc) are provisioned manually and shared by multiple teams. The team is unable to modify configuration which they want to test adhoc and needs to raise change requests. | 0
Continuous Integration | Artisan | 60 | Source code is under version management | The source code is checked in to a version control tool even though the team commits are very infrequent. | 54
Continuous Integration | Artisan | 61 | Build is automated and tests are run as part of the build | There's a script to build the application and this process is automated. There are also tests run as part of the build process. | 56
Continuous Integration | Artisan | 62 | Testing partially automated, and code coverage greater than 0 | There are some test cases but not all of them have been automated. The test coverage is greater than zero but less than 50%. Team needs to improve on the test coverage and move it towards 50%. Team also needs to automate the test cases they have (this will need to be prioritised in the backlog as well and some slack put in the system to cater for this) | 58
Continuous Integration | Expert | 63 | Team checks code into version management system on daily basis. | The team checks in code every day to the version management tool. Team still works on several long-lived branches but the code is checked in at least once a day. Team needs to start moving towards very short lived branches | 60
Continuous Integration | Expert | 64 | All artefacts are under version management. | All the artefacts such as packages, build scripts, etc are checked in to the version management system. Every new team member can check out the source code and build the application from the version management system. | 60
Continuous Integration | Expert | 65 | Build and Deployment to development environment are automated. | Deployment of the application to the development environment is automated and happens without any manual steps. Requires a human to trigger the build. | 55,61
Continuous Integration | Expert | 66 | Anyone in the team can start build at any point in time | Builds are triggered by simple click of a button on the continuous integration management tool. | 57
Continuous Integration | Expert | 67 | Build status and broken builds are visible to all. | Build status are shown on dashboards which the team can see. Team has a view of the broken builds history. Team continues with coding tasks even when the build is broken. The team needs to start moving towards a state where a broken build leads to a stop in new functionality until the build is fixed (Think Broken Window Syndrome). | 0
Continuous Integration | Expert | 68 | Testing partially automated – greater than 50% code coverage. | The test coverage is greater than 50% but not entirely covered. Team needs to improve on the test coverage and move it towards 90 - 100% coverage. Team fails the build if the coverage metric is not met. | 62
Continuous Integration | Expert | 69 | Release and Change Management partially automated. | There are manual steps for the release of the application (these can be automated but are not yet automated). | 0
Continuous Integration | Professional | 70 | Automated build and test cycle every time a change is committed | Every commit from a team member triggers a build and test stage in the continuous integration management tool. | 65
Continuous Integration | Professional | 71 | Build metrics gathered, visible, and acted on. | The build metrics are visible on dashboards in the team space. Static code analysis metrics are also visible on the dashboards and the team actively works to improve the code metrics. | 0
Continuous Integration | Professional | 72 | Builds are not left broken and code is not committed on a broken build. | Broken builds are attended to. Team has adopted the practice of "Don't push on a broken build" and "You break it, you fix it or revert to the last build that passed" | 0
Continuous Integration | Professional | 73 | Deployment to test environment is automated. | Deployment of the application to the test environment is automated and happens without any manual steps. Requires no human to trigger the build. | 68
Continuous Integration | Professional | 74 | Non-functional testing is automated. | There is a continuous integration pipeline and non-functional requirements are tested. For customer facing or critical applications, there is inclusion of security testing as part of the pipeline. For applications that require high resilience, this is tested as part of the pipeline and the statistics are shown on the team dashboards. | 68
Continuous Integration | Professional | 75 | Testing is automated as much as is practical. | Tests that can be automated are automated. The only unautomated tests are the manual exploratory edge cases which have no value in being automated and should preferably be left manual. Unit tests, integration tests, scenario-based tests, consumer contract tests and other significant flow tests are all automated. | 68
Continuous Integration | Professional | 76 | Environments can be provisioned at on demand. | Environments are provisioned on demand using automated tools like Chef. The teams can provision these environments and do not need to go through a rigorous process to obtain such environments. The team also has full access to such environments | 59
Continuous Integration | Master | 77 | Build and deployment are automated as much as is practical | The build and deployment processes are automated as much as the constraints allow. This should be automated preferably all the way to production, however, in some organisations this may not be possible. The steps to production exists and can be triggered manually on receiving the requisite approvals. | 70
Continuous Integration | Master | 78 | The build pipeline extends directly into production | The team has a build pipeline that extends directly to production. Artefacts and code can be promoted through various environments all the way to production. | 70
Continuous Integration | Master | 79 | Tests are run in parallel across multiple machines | To speed up the regression tests feedback, the teams have parallelized the tests suites across multiple machines. | 73,74,75
Continuous Integration | Master | 80 | Trunk-based development is the standard practice and integration happens continuously. Branches are rarely created and are short lived. | The team performs Continuous Integration in its truest form with short-lived branches and trunk-based development as the modus operandi. Branches are only used for exploration and short feature delivery but merged to the master branch and deleted as soon as the work is complete. | 0
Continuous Integration | Master | 81 | Check-ins occur multiple times each day. | Team members check-in code multiple times each day. The check-ins have very small batches of changes and are very frequent usually having less than a few hours worth of work. | 0
Continuous Integration | Master | 82 | Environment & infrastructure specifications are managed and versioned along with all other artefacts. | All the environment and infrastructure specifications are treated similarly to code. They are managed and versioned and can be rebuilt from the version control management system entirely. | 76
Continuous Integration | Master | 83 | The CI build creates and provisions environments to allow scalability for testing. | Team uses the build pipelines and continuous integration tools to provision infrastructure on demand. The team is able to provision and destroy environments without dependence on several external teams. | 76
Continuous Integration | Master | 84 | Release and Change Management fully integrated into deployment processes. | The release and change management process is catered for in the deployment process. Parts of the build pipeline address the governance around release and change management and the deployment process auto-generates the documentation required for the process. | 69
Continuous Integration | Master | 85 | The product is always in releasable state. | As is required by continuous integration practices, the software product is always in a releasable state. The build pipeline is in a green (no failing tests/broken builds) state and every broken build state is fixed immediately or reverted to ensure that the application is in a releasable state always. | 69
Continuous Integration | Master | 86 | Automated release process, release to customers is a business decision. | Release to the customers is a business decision rather than a technology decision. Business can trigger the release if they are happy with the functionality and technology is not a bottleneck for timeous customer releases. The process is automated with business being able to release themselves should they want to. | 69
Incident Management | Traveller | 87 | The process for handling problems and incidents is ad-hoc. | Current process for handling incidents is ad-hoc. The team needs to start instituting an incident management process and document it so it is easily accessible by all the team members. | 0
Incident Management | Artisan | 88 | An incident management process is in place and understood. | An incident management process is documented and in place. The team knows where to find the document and uses it to manage incidents. Incidents are also recorded on the team wall. | 87
Incident Management | Artisan | 89 | Key people are identified for incident management. | There are key people identified to handle incidents and this is well known by the team. | 87
Incident Management | Artisan | 90 | The number of handoffs and teams involved in incident resolution is minimal. | There is very minimal handoffs. The resolution is effective and insolves very few teams, generally the core team and the dependent system team. | 0
Incident Management | Expert | 91 | Incidents and problems feed into backlog | The incidents are recorded in the team backlog and prioritised together with all the other work in flight. There is an understanding of incident classification and the turn around time for the different classes of incidents. The team reacts appropriately based on the class of the incident. | 88
Incident Management | Expert | 92 | Operation requirements are identified and tracked in the backlog | Operational requirements for the application are identified and tracked in the backlog. Some of these requirements are MTTR, System Downtime, Service/Application response times, Service/Application downtime etc. These are displayed in dashboards in the team area. | 89
Incident Management | Expert | 93 | Problem management includes an urgency to address the root cause | The team is encouraged to address the root cause of the incidents/problems. The tasks are prioritised, estimated and planned within the iteration to give the team enough time to address the root cause. | 0
Incident Management | Expert | 94 | Root cause analysis is consistently performed. | Root cause analysis is performed for each incident. | 0
Incident Management | Expert | 95 | Level 1, 2, 3 support structure in place | The different support levels are in place and known by the team and stakeholders. | 90
Incident Management | Expert | 96 | Instrumentation (monitoring) in place. | Team has implemented monitoring and alerting for the applications they are working on. This proactively lets the team know of any incidents before the stakeholders inform the team and the team strives to resolve incidents before they become evident to the stakeholders. | 0
Incident Management | Professional | 97 | Defects are resolved once and deployed automatically across all environments. | Defect management is automated and follows the same continuous integration life cycle as features. | 91,92
Incident Management | Professional | 98 | Defects resolution includes full regression tests | For each defect, a test is written which is run on completion of the defect resolution as part of the regression suite to ensure that the defect does not re-occur or the team is notified if it re-occurs. | 91,92
Incident Management | Professional | 99 | System health is proactively monitored. | The system health is proactively monitored and displayed on dashboards in the team space. Some health status include MTTR, downtime, application response times, concurrent connections etc. | 91,92
Incident Management | Professional | 100 | Root cause analysis is highly valued and regularly trended. | The root cause analysis tasks are tracked and recorded so the team has a history of them. | 93,94
Incident Management | Master | 101 | Feature teams do own incident management | Each feature team does their own incident management as opposed to a centralised incident management team distributing tasks to the various teams. | 97,98,99
Incident Management | Master | 102 | Fail Forward (failing in a way that enables you to identify and overcome underlying problem, encapsulates the way forward and reduce the likelihood of failure the next time around) | The culture in the team is to fail forward. Incidents are managed, tracked and documented to ensure they are not repeated. Test cases are put in place to reduce the likelihood of failure. | 97,98,99
Incident Management | Master | 103 | Team actively manages, monitors and reviews what happens in production, feedback loop is enabled and acted on. | The feature teams have dashboards monitoring the state of the application in production and uses the feedback from the monitoring to drive tasks for operational optimisation. | 96
Risk and Issue Management | Traveller | 104 | Risk Management does not exist or is just a box to tick in order to get through a process (i.e. something done to keep risk and audit people happy). | To be at this level, the team does not have a risk management process in place and simply does compliance with audits by ticking check boxes without necessarily implementing any processes to avert risk. To move from this level the team needs to start identifying, managing and tracking risk. | 0
Risk and Issue Management | Traveller | 105 | There is no awareness or transparency of current risks and issues in the team. | The team at this level is unable to clearly articulate what the risks are. The various risks are not transparent to the team and may be known by very few individuals within the team. | 0
Risk and Issue Management | Artisan | 106 | Risks have been identified and are captured using an appropriate artefact such as a risk story wall or risk register. | At this level, risks are captured by the team and tracked on the team wall and/or story management system. The team members can access the various risks and are all aware of what they are. | 104
Risk and Issue Management | Artisan | 107 | Each identified risk has been assigned a risk mitigation or action plan. | The risks are allocated owners as well as mititgation/action plans. These are clearly captured in the story management system. | 105
Risk and Issue Management | Artisan | 108 | Risks are discussed as part of the iteration planning process. | The risks are discussed and reviewed as part of the iteration planning process and action items are allocated and assigned to prospective risk item owners. These are then tracked and reviewed throughout the iteration to ensure mitigation is in place. | 105
Risk and Issue Management | Expert | 109 | Risks, issues and blockers are discussed and updated in appropriate detail as part of all sessions (stand-ups; iteration planning; showcases; steering committee meetings) | Risks items are discussed during the agile ceremonies such as standups and they are updated accordingly to ensure they are not just recorded but are also mitigated. Any blockers are highlighted and addressed. | 106
Risk and Issue Management | Expert | 110 | Unmitigated or uncontrollable risks are easily identifiable. | The team is able to identify/raise risks that do not have a mitigation plan and assign an owner, while recording on the wall. | 107108
Risk and Issue Management | Expert | 111 | Risks, controls and action plans are assigned to appropriate owners: someone who understand the risk, has responsibility and accountability for managing the risk, and has the authority to implement controls and actions. | All the risks have appropriate owners. Owners update during daily stand-ups on the progress towards mitigating the risks. | 0
Risk and Issue Management | Professional | 112 | The cost and benefits of risk mitigations are evaluated and recorded before they are implemented. | Cost benefit analysis of risk mitigations are discussed in the iteration planning sessions before risks are prioritised. | 110
Risk and Issue Management | Professional | 113 | Risk management roles, responsibilities and accountabilities have been defined and agreed upon. | Roles, responsibilities and accountabilities for the risks owners are defined, agreed upon and documented where it is accessible by all team members. | 111
Risk and Issue Management | Professional | 114 | Regular check points with Business Stakeholders to ensure they are aware of all risks and issues. | There is clear communication with the business stakeholders and different stakeholders on the risks and mitigation plans in progress. | 0
Risk and Issue Management | Master | 115 | Risk mitigations and actions are explicitly designed to increase positive outcomes and reduce negative outcomes. | The team explicitly designs the risk mitigation and actions and are proactive rather than reactive towards the potential of risks. | 112
Risk and Issue Management | Master | 116 | The business participates in developing mitigation strategies | Business stakeholders are also involved in the risks mitigation strategies and are aware of the effect of the various risks. | 113
Risk and Issue Management | Master | 117 | Risk management is used to identify potential opportunities and drive strategy by thinking about risk in terms of uncertainty (which could be positive or negative) | Risk management is used to identify potential opportunities and these are recorded in the story management system linking them to the risks. There is openess with respect to raising and highlighting risks and using them to inform the strategy. | 0
Risk and Issue Management | Master | 118 | Measures and metrics exist to demonstrate the effectiveness of risk management and where improvement is required. | The risks resolutions are measured and used to optimise the risk management process. | 0
Risk and Issue Management | Master | 119 | The financial impact of risk and issues is clearly understood. | Financial impact of the risks are captured and availed to stakeholders and the team to drive more effective and optimised risk management. | 0
Software Design | Traveller | 120 | Speculative design and technical decisions are made on an ad hoc basis. There is no vision or long team technical planning. |  | 0
Software Design | Traveller | 121 | BDUF = Big Design Up-Front |  | 0
Software Design | Traveller | 122 | Solutions are tightly coupled and brittle |  | 0
Software Design | Artisan | 123 | Regular design reviews in place |  | 120
Software Design | Artisan | 124 | Design assumptions are tracked and validated during iterations |  | 121
Software Design | Expert | 125 | Design issues are tracked and prioritised in the backlog. |  | 123
Software Design | Expert | 126 | Non-functional requirements are documented and tracked. |  | 124
Software Design | Expert | 127 | Clear interfaces defined between modules. |  | 122
Software Design | Expert | 128 | Design is owned by the team. |  | 0
Software Design | Professional | 129 | There is a partial traceability between design and requirements. |  | 125
Software Design | Professional | 130 | Design requirements are expressed as automated tests. |  | 0
Software Design | Professional | 131 | Non-functional requirements are defined and associated metrics tracked automatically. |  | 126
Software Design | Professional | 132 | Where practical all modules of the system can be simulated. |  | 127
Software Design | Professional | 133 | Where possible design is captured in a model and code generated. |  | 0
Software Design | Master | 134 | There is full traceability between design and requirements. |  | 129
Software Design | Master | 135 | Design activities are performed on a Just In Time basis. |  | 0
Teaming | Traveller | 136 | The team cannot make decisions without consultation . |  | 0
Teaming | Traveller | 137 | The teams goals and visions are unclear. |  | 0
Teaming | Traveller | 138 | The team doesn't clearly understand the entire stakeholder landscape. |  | 0
Teaming | Artisan | 139 | Team vision and goals are agreed, captured and understood. |  | 137
Teaming | Artisan | 140 | There is a clear understanding of who are the teams stakeholders. (Consumers, partners and clients). |  | 138
Teaming | Artisan | 141 | There is a clear definition of what the teams success is (definition of ‘done’). |  | 0
Teaming | Expert | 142 | The team actively seeks feedback in an effort to achieve the goals |  | 139
Teaming | Expert | 143 | Transparency and high level of collaboration within the team are in place. |  | 0
Teaming | Expert | 145 | Impact of blockers and dependencies are minimised and managed and the team knows what these are. |  | 141
Teaming | Professional | 146 | Balanced participation is in place. Team members contribute as appropriate and each members opinion is valued. |  | 143
Teaming | Professional | 147 | Team uses adequate measures to monitor success. |  | 145
Teaming | Master | 148 | All decision-making is internal to the team |  | 136
Teaming | Master | 149 | Complete collective ownership is in place, both when team is successful and when it fails, |  | 146
Teaming | Master | 150 | Team is actively improving. Retrospectives are driving improvement. |  | 147
Release Management | Traveller | 151 | Cycle time is extremely long. |  | 0
Release Management | Traveller | 152 | Deployment is mostly manual, very complex and requires high level of coordination between stakeholders on the day of the release |  | 0
Release Management | Traveller | 153 | Pace and delivery of work is inconsistent throughout the release cycle |  | 0
Release Management | Traveller | 154 | Separate build artefacts are created for each environment |  | 0
Release Management | Artisan | 155 | Releases are planned to a regular cycle and features are tracked and managed to the regular time frame. |  | 151
Release Management | Artisan | 156 | Planned release dates are seldom moved out. |  | 152
Release Management | Artisan | 157 | The process for handing the release to operations and support teams is in place. |  | 0
Release Management | Artisan | 158 | Standard build artefacts are defined and produced (release notes, binaries, configurations, test coverage reports...) |  | 154
Release Management | Expert | 159 | Releases and deployments are mostly automated (might require manual configuration and coordination between teams). |  | 155
Release Management | Expert | 160 | The confidence level for the release is high. |  | 156157
Release Management | Professional | 161 | Release notes are automatically generated. |  | 159
Release Management | Professional | 162 | Releases are not reliant on the knowledge of the key individuals. |  | 160
Release Management | Professional | 163 | Operations teams collaborate closely with the delivery team and contribute to minimize the risk of failure in production. |  | 160
Release Management | Professional | 164 | Release metrics and trends are tracked |  | 0
Release Management | Master | 165 | Releases can be deployed at any time and are fully automated. |  | 161
Release Management | Master | 166 | The team controls the release |  | 162
Release Management | Master | 167 | The product owner is able to determine when release goes into production |  | 161
Release Management | Master | 168 | Operations team is part of the product/program team |  | 163
Release Management | Master | 169 | Releases are Routine. No roll backs, always roll forward. |  | 0
Release Management | Master | 170 | Dark launching is enabled (Features can be released in switched of state). |  | 0
Quality Assurance | Traveller | 171 | Testing is manual |  | 0
Quality Assurance | Traveller | 172 | There is a high amount of rework due to testing late in the lifecycle. |  | 0
Quality Assurance | Traveller | 173 | Non-functional testing is not considered upfront. |  | 0
Quality Assurance | Traveller | 174 | Test cases are designed based only on the requirements document, mainly by testing team |  | 0
Quality Assurance | Traveller | 175 | Absence of unit/integration testing |  | 0
Quality Assurance | Traveller | 176 | There is very little reuse of Quality Assurance assets. |  | 0
Quality Assurance | Artisan | 177 | Regression test packs are partially automated |  | 171172173
Quality Assurance | Artisan | 178 | Regression packs run frequently but on an ad hoc basis |  | 171172173
Quality Assurance | Artisan | 179 | Test cases designed by the team, with testing, development and business analysts |  | 174
Quality Assurance | Expert | 180 | Regression test packs are fully automated |  | 177178
Quality Assurance | Expert | 181 | Regression test packs are run as part of the build |  | 177178
Quality Assurance | Expert | 182 | 50% coverage automated testing |  | 177178
Quality Assurance | Expert | 183 | Automated smoke testing is in place |  | 177178
Quality Assurance | Expert | 184 | Automated performance testing is in place |  | 177178
Quality Assurance | Expert | 185 | Non-functional requirements are defined and measured |  | 0
Quality Assurance | Expert | 186 | Test cases designed by the team as part of the iteration |  | 179
Quality Assurance | Expert | 187 | Unit tests are created using TDD. |  | 0
Quality Assurance | Professional | 188 | Automated infrastructure testing is in place |  | 180181182183184
Quality Assurance | Professional | 189 | Automated security testing is in place |  | 180181182183184
Quality Assurance | Professional | 190 | Tests are automated as much as is practical |  | 180181182183184
Quality Assurance | Professional | 191 | Quality metrics and trends are tracked |  | 0
Quality Assurance | Professional | 192 | Anyone can execute the tests. |  | 0
Quality Assurance | Master | 193 | Active process is in place to understand root cause and respond to it. |  | 0
Quality Assurance | Master | 194 | Test artefacts are treated with the same importance as code and continually refactored and maintained. |  | 186
Quality Assurance | Master | 195 | Performance testing metrics are defined early in the process. |  | 191
Quality Assurance | Master | 196 | Tests drive release readiness |  | 0
Environments | Traveller | 197 | Data migrations un-versioned and performed manually. |  | 0
Environments | Traveller | 198 | Test data is not controllable |  | 0
Environments | Traveller | 199 | Environments are heavily governed |  | 0
Environments | Traveller | 200 | Environments are not refreshed regularly |  | 0
Environments | Traveller | 201 | Test environments and test data are frequently unavailable |  | 0
Environments | Traveller | 202 | Environments are provisioned manually |  | 0
Environments | Traveller | 203 | Key man dependencies |  | 0
Environments | Artisan | 204 | Changes to database are done with automated scripts versioned with application |  | 197
Environments | Artisan | 205 | A separate test environment is available. |  | 198199200201
Environments | Artisan | 206 | Test environment is shared with other teams. |  | 198199200201
Environments | Artisan | 207 | An external group maintains the environment. |  | 198199200201
Environments | Artisan | 208 | Test environments are available during specific dates/time slots |  | 198199200201
Environments | Artisan | 209 | Ability to deploy basic virtual environments |  | 0
Environments | Artisan | 210 | Team has a dedicated development environment |  | 0
Environments | Expert | 211 | Database changes are performed automatically as part of deployment process. |  | 204
Environments | Expert | 212 | Test environments are readily available. Can be reproduced with manual work + coordination between operational teams. |  | 205206207208
Environments | Expert | 213 | Access to a production-like environment is restricted to a small group of closely-related application teams, and delays at this level are unusual. |  | 0
Environments | Expert | 214 | Environment provisioning partially automated. |  | 202
Environments | Expert | 215 | Some virtual environments have interfaces available ‘stubs’ to run end-to-end testing. |  | 209
Environments | Professional | 216 | Database upgrades and rollbacks are tested with every deployment |  | 211
Environments | Professional | 217 | Database performance is monitored and optimized. |  | 211
Environments | Professional | 218 | Minimal manual work is required to replicate and configure environments but this can be completed within hours. |  | 212213
Environments | Professional | 219 | Multiple test environments are readily available for the exclusive use of the team, including a production-like environment that’s allows a reasonable level of non-functional and cross-system integration testing and reliable acceptance testing. |  | 212213
Environments | Professional | 220 | Dev workstations are easily configured and can be built in an automated manner. |  | 0
Environments | Professional | 221 | Virtual environments have all interfaces available ‘stubs’ to run end-to-end testing |  | 215
Environments | Master | 222 | Data and environments are treated as code, versioned and frequently re-loaded |  | 216217
Environments | Master | 223 | Release to release feedback loop of database performance and deployment process is in place. |  | 216217
Environments | Master | 224 | Proactive monitoring is in place with shortest possible time to resolve failure. |  | 216217
Environments | Master | 225 | IP is built into the process, including automated deployment, provisioning, configurations and data. Integral part of the build pipeline. |  | 218219
Environments | Master | 226 | Environments are managed by the team, the team able to create complete simulated environment on demand |  | 218219
Environments | Master | 227 | All environments are managed effectively |  | 218219
Environments | Master | 228 | Provisioning is fully automated |  | 214
Environments | Master | 229 | Main dependencies are simulated across the board |  | 0
Environments | Master | 230 | Virtualization is used if applicable. |  | 221
Feature teams | Traveller | 231 | The team doesn’t have all cross-functional and cross-component knowledge and skills to complete end-to-end customer feature. |  | 0
Feature teams | Traveller | 232 | The team members are not dedicated. |  | 0
Feature teams | Traveller | 233 | The is a low level of collaboration between team members. |  | 0
Feature teams | Traveller | 234 | There are multiple handoffs and dependencies on the external teams and stakeholders. |  | 0
Feature teams | Artisan | 235 | The key skills are part of the team. This includes cross-functional and cross-component skills. |  | 231232
Feature teams | Artisan | 236 | Handoffs are identified. |  | 234
Feature teams | Artisan | 237 | Triad is established across three functions, quality, product and technical. Triad is committed to execute a strategy together that gets specific, intended results. |  | 0
Feature teams | Expert | 238 | The team members are dedicated to the team. |  | 232
Feature teams | Expert | 239 | Cross-functional and cross-component skills are within the team, the team works on a complete feature, across all components and disciplines (analysis, programming, testing, …) |  | 235
Feature teams | Expert | 240 | New members are efficiently integrated into feature team. |  | 235
Feature teams | Expert | 241 | Triad is fully-functioning and not dependent on external validation and external authority. |  | 237
Feature teams | Expert | 242 | Goals are clearly prioritized and timeously achieved |  | 0
Feature teams | Professional | 243 | T-shaped skills emerge (team members can perform more than one function) |  | 239240
Feature teams | Professional | 244 | The team is self-organizing. The team is self-managed and has necessary autonomy to modify the design of their team and/or aspects of the organisational context in which the operate. |  | 239240
Feature teams | Professional | 245 | Metrics are in place to ensure constant improvement. |  | 242
Feature teams | Master | 246 | All decision-making is internal to the team, who can make decisions on how to deliver artefacts, and as to quality measures applied to artefacts. |  | 243244
Feature teams | Master | 247 | T-shaped skill profile is a majority. |  | 243244
Feature teams | Master | 248 | Team is responsible for all aspects of feature delivery, from equipment requisition to production. |  | 243244
Feature teams | Master | 249 | Continuous improvement is in place, driven by retrospectives within the team and across the teams |  | 245